## Project Planner
myClassroom
| Current Week: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  | Actual (beyond plan) | % Complete (beyond plan) | ***NOTE*** Chart assumes 4 developers and 2 designers at 40 hours a week
ACTIVITY |  | WEEKS
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Design Web | 0% | bar: WEEKS 1 to WEEKS 2
Develop Web API | 0% | bar: WEEKS 3 to WEEKS 6
Develop Web Design | 0% | bar: WEEKS 3 to WEEKS 4
Design Mobile | 0% | bar: WEEKS 5 to WEEKS 6
Develop Mobile API | 0% | bar: WEEKS 7
Develop Mobile App | 0% | bar: WEEKS 8 to WEEKS 10
Design Comm. Service | 0% | bar: WEEKS 7 to WEEKS 8
Dev. Comm. Service | 0% | bar: WEEKS 11 to WEEKS 13
Design Grade Service | 0% | bar: WEEKS 9 to WEEKS 10
Dev. Grade Service | 0% | bar: WEEKS 14 to WEEKS 16